|  | SWMC |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| DATE COMPLETED: |  |  |  |  |  |  |  | ## TEAM MEMBERS |  |  |
|  | Plan-Do-Check-Act |  |  |  |  |  |  |  |  |  |
| PROBLEM STATEMENT: | How to decrease falls on Med/Surg 4th? |  |  |  |  |  |  |  | Mirella Buchman |  |
|  |  |  |  |  |  |  |  |  | M/S 4 Staff |  |
| GOAL: | Med/Surg 4 will reduce falls to less than or equal to two per quarter. All Med/Surg staff will implement new interventions and start education by March 12th. All falls will be tracked by using QRRs. By the end of Q2, May 31st, med/surg unit will have less than or equal to two falls for that quarter. Med/Surg 4 will provide safe care and reduce patient harm related to falls. |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | 4. |  |  |
| ROOT CAUSE(S): |  |  |  |  |  |  |  |  |  |  |
| Mis/lack of education |  |  |  |  |  |  |  |  |  |  |
| BARRIER(S): |  |  |  |  |  |  |  | External |  |  |
| 1.New staff |  |  |  |  |  |  |  |  |  |  |
| 2.Old Habits |  |  |  |  |  |  |  |  |  |  |
| 3.Not using equipment appropriately |  |  |  |  |  |  |  |  |  |  |
| 4.Not using Nurse Call appropriately |  |  |  |  |  |  |  |  |  |  |
| 5. |  |  |  |  |  |  |  |  |  |  |
| METRIC(S) |  | Pre-intervention | First Remeasurement | Second Remeasurement |  | Final Remeasurement | COMMENTS |  |  |  |
| Number of Falls |  | 1/1/-3/17/21 9 inpatient falls 5/9 Medical (56%) | 3/17-4/30/21 4 inpatient falls 0/4 Medical (0%) | 5/1-5/30/21 8 inpatient falls 4/8 Medical (50%) |  |  | 5/1-5/30-two of those were assisted to the floor by family/staff due to diagnosis. Last fall 5/29/21-assisted pt to ground. |  |  |  |
| TASKS |  | RESPONSIBLE TEAM MEMBER | START DATE | ESTIMATED COMPLETION DATE |  | ACTUAL COMPLETION DATE | COMMENTS (STATUS, OUTCOMES, EVALUATION, ETC.) |  |  |  |
| No Pass Zone |  | NM | 1/1/21 | On going |  |  | 4/5-educated directors -educated Administration -Educated MIS |  |  |  |
| Safety Huddles Bed orientation |  | Charge Nurses | 2/15/21 | On going |  |  |  |  |  |  |
| # BSSR |  | ALL | 1/1/21 | On going |  |  |  |  |  |  |
| Hourly Rounding |  | ALL | 1/1/21 | On going |  |  |  |  |  |  |
| Nurse Leader Rounding |  | NM/Charges | 1/28/21 | On going |  |  |  |  |  |  |
| Morse Scale Education |  | NM | 2/15 | 3/10/21 |  | 3/10/21 |  |  |  |  |
| White Boards |  | All | 2/15/21 | On going |  |  | State safety score and fall risk |  |  |  |
| Bed/chair alarms |  | All | 2/15/21 | On going |  |  | All Mod-High fall risk will have |  |  |  |
| Nurse Call Light |  | All | 2/15/21 | On going |  |  | All beds plugged into call light system |  |  |  |
| Mod/high fall risk will have all high fall risk interventions |  | ALL | 3/10/21 | On going |  |  | Staff will stay in bathroom w/ mod to high fall risk patients |  |  |  |
| Bathroom signs |  | NM |  |  |  |  |  |  |  |  |
| Gait/Transfer training |  |  | 6/7/21 6/9/21 | 6/9/21 |  |  | 79 employees participated. 13/79 Medical |  |  |  |
| Gaitbelt Hooks added by bathroom to all rooms |  | Reyna and Nichole |  |  |  | 4/1/21 | Easy access for DI/PT |  |  |  |
| Post fall Huddles |  | NM |  |  |  |  |  |  |  |  |
| Stickers added to ceiling |  | Plant ops/Jennifer |  |  |  | 7/1/21 | “Call don’t fall” |  |  |  |
| Fall Presentation at unit meeting |  | NM |  |  |  | 7/1/21 7/2/21 | Power point created by Joel. |  |  |  |
| Selected Definitions: Metric – units of measure used to evaluate a process and determine change in the process or outcomes related to it over time Root Causes – reasons that a process is not functioning as designed Barriers – impediments to changing a process or to improving the outcomes related to that process Brainstorming – a structured group session to generate a list of ideas about an issue in a short period of time |  |  |  |  |  |  |  |  |  |  |